## Setup
Current Year | 2016
11/1/2016 | 12/1/2016 | 1/1/2017
Category | Occurance | Day | Month | Absolute | Date
Thanksgiving | Last | Thursday | November |  | 2016-11-24
Decorate | Last | Friday | November |  | 2016-11-25
Gifts Teacher | 1 | Saturday | December |  | 2016-12-03
Cards | 2 | Saturday | December |  | 2016-12-10
Calendars | 2 | Saturday | December |  | 2016-12-10
Gifts | 3 | Saturday | December |  | 2016-12-17
Gifts Extended | 3 | Saturday | December |  | 2016-12-17
Cookies | 3 | Saturday | December |  | 2016-12-17
Christmas |  |  | December | 25 | 2016-12-25
New Year Party |  |  | December | 31 | 2016-12-31
New Year |  |  | January | 1 | 2016-12-01
Formulas:
Date = IF(Table2[[#This Row],[Category]]<>"",DATE(YEAR(A2),MONTH(A2)+1,0)+MOD(-WEEKDAY(DATE(YEAR(A2),MONTH(A2)+1,0),2)-3,-7),"")
Date = IF(Table2[[#This Row],[Category]]<>"",B2+(7*[Occurance])-WEEKDAY(B2),"")

## Tasks
Task | Subtask | Tminus | Target Date | Scheduled Date
Calendars | Select pictures | 14 | 2016-12-10 | 2016-11-26
Calendars | Layout months 1-3 | 10 | 2016-12-10 | 2016-11-30
Calendars | Layout months 4-6 | 8 | 2016-12-10 | 2016-12-02
Calendars | Layout months 7-9 | 6 | 2016-12-10 | 2016-12-04
Calendars | Layout months 10-12 | 4 | 2016-12-10 | 2016-12-06
Calendars | Order calendars | 0 | 2016-12-10 | 2016-12-10
Cards | Update addresses | 14 | 2016-12-10 | 2016-11-26
Cards | Make lists | 13 | 2016-12-10 | 2016-11-27
Cards | Pull CSV | 12 | 2016-12-10 | 2016-11-28
Cards | Write email | 10 | 2016-12-10 | 2016-11-30
Cards | Write letter | 9 | 2016-12-10 | 2016-12-01
Cards | Make labels | 7 | 2016-12-10 | 2016-12-03
Cards | Print newsletters | 6 | 2016-12-10 | 2016-12-04
Cards | Set up e-cards | 5 | 2016-12-10 | 2016-12-05
Cards | Stuff envelopes | 4 | 2016-12-10 | 2016-12-06
Cards | Stamp and mail | 0 | 2016-12-10 | 2016-12-10
Christmas | Make grocery list | 30 | 2016-12-25 | 2016-11-25
Christmas | Plan menu | 30 | 2016-12-25 | 2016-11-25
Christmas | Buy food | 14 | 2016-12-25 | 2016-12-11
Christmas | Buy food | 7 | 2016-12-25 | 2016-12-18
Christmas | Make schedule | 7 | 2016-12-25 | 2016-12-18
Christmas | Make pies | 1 | 2016-12-25 | 2016-12-24
Christmas | Cook | 0 | 2016-12-25 | 2016-12-25
Cookies | Plan cookies | 30 | 2016-12-17 | 2016-11-17
Cookies | Buy supplies | 14 | 2016-12-17 | 2016-12-03
Cookies | Make cookies | 0 | 2016-12-17 | 2016-12-17
Decorate | put up decorations | 0 | 2016-11-25 | 2016-11-25
Gifts | Get lists | 30 | 2016-12-17 | 2016-11-17
Gifts | Shop | 15 | 2016-12-17 | 2016-12-02
Gifts | Stocking stuffers | 5 | 2016-12-17 | 2016-12-12
Gifts | Wrap | 1 | 2016-12-17 | 2016-12-16
Gifts Extended | Buy | 30 | 2016-12-17 | 2016-11-17
Gifts Teacher | Decide on gifts | 30 | 2016-12-03 | 2016-11-03
Gifts Teacher | Wrap | 7 | 2016-12-03 | 2016-11-26
Gifts Teacher | Send gifts | 5 | 2016-12-03 | 2016-11-28
New Year | Make grocery list | 30 | 2016-12-01 | 2016-11-01
New Year | Plan menu | 30 | 2016-12-01 | 2016-11-01
New Year | Buy food | 14 | 2016-12-01 | 2016-11-17
New Year | Buy food | 7 | 2016-12-01 | 2016-11-24
New Year | Make schedule | 7 | 2016-12-01 | 2016-11-24
New Year | Make pies | 1 | 2016-12-01 | 2016-11-30
New Year | Cook | 0 | 2016-12-01 | 2016-12-01
New Year | Setup calendar for next year | 0 | 2016-12-01 | 2016-12-01
New Year | Take down decorations | 0 | 2016-12-01 | 2016-12-01
New Year Party | Make guest list | 30 | 2016-12-31 | 2016-12-01
New Year Party | Send invitations | 14 | 2016-12-31 | 2016-12-17
New Year Party | Decide on food | 10 | 2016-12-31 | 2016-12-21
New Year Party | Buy food | 3 | 2016-12-31 | 2016-12-28
New Year Party | Clean | 2 | 2016-12-31 | 2016-12-29
New Year Party | Food prep | 0 | 2016-12-31 | 2016-12-31
New Year Party | Setup | 0 | 2016-12-31 | 2016-12-31
Thanksgiving | Make grocery list | 30 | 2016-11-24 | 2016-10-25
Thanksgiving | Plan menu | 30 | 2016-11-24 | 2016-10-25
Thanksgiving | Buy food | 14 | 2016-11-24 | 2016-11-10
Thanksgiving | Buy food | 7 | 2016-11-24 | 2016-11-17
Thanksgiving | Make schedule | 7 | 2016-11-24 | 2016-11-17
Thanksgiving | Thaw turkey | 4 | 2016-11-24 | 2016-11-20
Thanksgiving | Make pies | 1 | 2016-11-24 | 2016-11-23
Thanksgiving | Cook | 0 | 2016-11-24 | 2016-11-24
Formulas:
Target Date = IF(Table1[[#This Row],[Task]]<>"",VLOOKUP([Task],Setup!$A4:F15,6, FALSE),"")
Scheduled Date = IF(Table1[[#This Row],[Target Date]]<>"",[Target Date]-[Tminus],"")

## RTM
Calendars - Select pictures 11/26/2016 #Holiday
Calendars - Layout months 1-3 11/30/2016 #Holiday
Calendars - Layout months 4-6 12/02/2016 #Holiday
Calendars - Layout months 7-9 12/04/2016 #Holiday
Calendars - Layout months 10-12 12/06/2016 #Holiday
Calendars - Order calendars 12/10/2016 #Holiday
Cards - Update addresses 11/26/2016 #Holiday
Cards - Make lists 11/27/2016 #Holiday
Cards - Pull CSV 11/28/2016 #Holiday
Cards - Write email 11/30/2016 #Holiday
Cards - Write letter 12/01/2016 #Holiday
Cards - Make labels 12/03/2016 #Holiday
Cards - Print newsletters 12/04/2016 #Holiday
Cards - Set up e-cards 12/05/2016 #Holiday
Cards - Stuff envelopes 12/06/2016 #Holiday
Cards - Stamp and mail 12/10/2016 #Holiday
Christmas - Make grocery list 11/25/2016 #Holiday
Christmas - Plan menu 11/25/2016 #Holiday
Christmas - Buy food 12/11/2016 #Holiday
Christmas - Buy food 12/18/2016 #Holiday
Christmas - Make schedule 12/18/2016 #Holiday
Christmas - Make pies 12/24/2016 #Holiday
Christmas - Cook 12/25/2016 #Holiday
Cookies - Plan cookies 11/17/2016 #Holiday
Cookies - Buy supplies 12/03/2016 #Holiday
Cookies - Make cookies 12/17/2016 #Holiday
Decorate - put up decorations 11/25/2016 #Holiday
Gifts - Get lists 11/17/2016 #Holiday
Gifts - Shop 12/02/2016 #Holiday
Gifts - Stocking stuffers 12/12/2016 #Holiday
Gifts - Wrap 12/16/2016 #Holiday
Gifts Extended - Buy 11/17/2016 #Holiday
Gifts Teacher - Decide on gifts 11/03/2016 #Holiday
Gifts Teacher - Wrap 11/26/2016 #Holiday
Gifts Teacher - Send gifts 11/28/2016 #Holiday
New Year - Make grocery list 11/01/2016 #Holiday
New Year - Plan menu 11/01/2016 #Holiday
New Year - Buy food 11/17/2016 #Holiday
New Year - Buy food 11/24/2016 #Holiday
New Year - Make schedule 11/24/2016 #Holiday
New Year - Make pies 11/30/2016 #Holiday
New Year - Cook 12/01/2016 #Holiday
New Year - Setup calendar for next year 12/01/2016 #Holiday
New Year - Take down decorations 12/01/2016 #Holiday
New Year Party - Make guest list 12/01/2016 #Holiday
New Year Party - Send invitations 12/17/2016 #Holiday
New Year Party - Decide on food 12/21/2016 #Holiday
New Year Party - Buy food 12/28/2016 #Holiday
New Year Party - Clean 12/29/2016 #Holiday
New Year Party - Food prep 12/31/2016 #Holiday
New Year Party - Setup 12/31/2016 #Holiday
Thanksgiving - Make grocery list 10/25/2016 #Holiday
Thanksgiving - Plan menu 10/25/2016 #Holiday
Thanksgiving - Buy food 11/10/2016 #Holiday
Thanksgiving - Buy food 11/17/2016 #Holiday
Thanksgiving - Make schedule 11/17/2016 #Holiday
Thanksgiving - Thaw turkey 11/20/2016 #Holiday
Thanksgiving - Make pies 11/23/2016 #Holiday
Thanksgiving - Cook 11/24/2016 #Holiday

## Explanations
Explanation of Formulas
Last Thursday of November
IF([@Category]<>"",DATE(YEAR($A$2),MONTH($A$2)+1,0)+MOD(-WEEKDAY(DATE(YEAR($A$2),MONTH($A$2)+1,0),2)-3,-7),"")
$a$2 holds the reference to the cell at the top that has the first day of November
DATE(YEAR($A$2),MONTH($A$2)+1,0) is the last day of November
MOD(-WEEKDAY(DATE(YEAR($A$2),MONTH($A$2)+1,0),2)-3,-7) subtracts the right amounth of days. The "-3" indicates we are looking for a Thursday
First Saturday of December
IF([@Category]<>"",$B$2+(7*B7)-WEEKDAY($B$2),"")
$b$2 holds the reference to the cell at the top that has the first day of November
(7*B7) gives you the appropriate week
-WEEKDAY($B$2) subtracts off the day of the week the month starts on, giving you the right date